## A1
A: Parental engagement and co-production 1: The widely held concern of parents that the local area is not able, or in some cases not willing, to meet their children’s needs
Measures/indicators of success | Data source | Frequency | Baseline | INTERIM (Sept/Oct combined data) OR Commentary | Targets & Actuals | [5 empty] | Responsibility for updating | Comments | RAG
Significant increase in the percentage of parents that agree or strongly agree with the confidence statements within the parental survey | Parental surveys | Six-monthly | 30.4% | Next version of the parent survey being designed & tested prior to rollout | December 2019 |  | June 2020 |  | December 2020 |  | Louise Burgess / Sharon McLoughlin | Next parental survey planned for deployment in early June, once we have shared the 'you said, we did' from the first survey
[5 empty] | Target |  | Target |  | Target
[5 empty] | 40% |  | 45% |  | 50%
[5 empty] | Actual |  | Actual |  | Actual
Increased use of the new online Local Offer | Number of hits on Local Offer when returned in search results | Six-monthly | Revised baseline Jan 18 - Dec 18 72,074 | 83,879 to the LO landing page (Nov 18 - Oct 19) | Target |  | Target |  | Target |  | Louise Burgess | Supporting statistics are also collected for individual months, and for page views
[5 empty] | 85000 |  | 90000 |  | 95000
[5 empty] | Actual |  | Actual |  | Actual
86532
SEN PEOs engage with an increased proportion of parents | SEN PEOs records of parental engagement | Termly | Baseline data (Aug-Nov 2019) PEO contact with 70 parents (Avg 17.5 per month) |  | Autumn 2019 | Spring 2020 |  | Summer 2020 |  | Autumn 2020 | Louise Burgess | Each Area to increase by 15 more parental contacts for advice re their concerns
[5 empty] | Target | Target |  | Target |  | Target
[6 empty] | 168 |  | +50 |  | +50
[5 empty] | Actual | Actual |  | Actual |  | Actual
108
Increased percentage of Year R-11-aged CYP with EHCPs placed in mainstream schools | Synergy | Termly | 45% in mainstream (SEN 2 Jan 2019 data) | SEN2 2020 Cohort | Target | Target |  | Target |  | Target | Katherine Atkinson
[5 empty] | 47% | 49% |  | 51% |  | 53%
[5 empty] | Actual | Actual |  | Actual |  | Actual
44.2%

## A2
A: Parental engagement and co-production 2: The limited role parents and carers (and YP) have in reviewing and designing services for children and young people with SEND
Measures/indicators of success | Data source | Frequency | Baseline | INTERIM (Sept/Oct combined data) OR Commentary | Targets & Actuals |  |  | Responsibility for updating | Comments | RAG
Significant increase in the percentage of parents that agree or strongly agree that they found information on the Local Offer useful | Parental surveys (To be supplemented by Local Offer website feedback) | Six-monthly | 19.2% | Next version of the parent survey being designed & tested prior to rollout | December 2019 | June 2020 | December 2020 | Louise Burgess / Sharon McLoughlin | Next parental survey planned for deployment in early June, once we have shared the 'you said, we did' from the first survey
[5 empty] | Target | Target | Target
[5 empty] | 30% | 35% | 40%
[5 empty] | Actual | Actual | Actual
Increased use of the new online Local Offer | Number of hits on Local Offer | Six-monthly | Revised baseline Jan 18 - Dec 18 72,074 | 83,879 to the LO landing page (Nov 18 - Oct 19) | Target | Target | Target | Louise Burgess | Supporting statistics are also collected for individual months, and for page views
[5 empty] | 85000 | 90000 | 95000
[5 empty] | Actual | Actual | Actual
86532
All governance forums and workstreams have identified and invited parent reps to all relevant meetings | Chairs/Leads | Short-term target | N/A | On track | Target |  |  | Louise Burgess
To be completed by September 2019

## B3
B: Inclusive Practice and the Outcomes, Progress and Attainment of Children and Young People 3: The variable quality of provision and commitment to inclusion in schools, and the lack of willingness of some schools to accommodate children and young people with SEND
Measures/indicators of success | Data source | Frequency | Baseline | INTERIM (Sept/Oct combined data) OR Commentary | Targets & Actuals | [5 empty] | Responsibility for updating | Comments | RAG | Notes
Reduced percentage of CYP with an EHCP subject to a fixed term exclusion | KCC Data | Termly | 8.9% (AY 2018-19) | 9.6% | Autumn 2019 | Spring 2020 |  | Summer 2020 |  | Autumn 2020 | Katherine Atkinson | 275 of 2,636 pupils excluded on one or more occasion. SEN provision of pupils sourced from Autumn 19 or Summer 19 or Spring 19 returns. The SEN provision of 15 pupils returned as 'unknown', thus these pupils and their exclusions have been excluded from the dataset and calculations. National comparator (2017-18) 8.03% |  | Sep 19 to Oct 19 - 129 of 1,343 pupils excluded. 32 pupils excluded from dataset and calculation due to SEN provision is 'unknown'.
[5 empty] | Target | Target |  | Target |  | Target
[5 empty] | 8% | 7% |  | 6% |  | 5%
[5 empty] | Actual | Actual |  | Actual |  | Actual
10.4%
Reduced number of CYP with an EHCP subject to a permanent exclusion | KCC Data | Termly | 5 (AY 2018-19) | 0 | Target | Target |  | Target |  | Target | Katherine Atkinson | Data currently for 4 months of the academic year so as data builds figure likely to rise.
[5 empty] | 1 | 1 |  | 0 |  | 0
[5 empty] | Actual | Actual |  | Actual |  | Actual
2
Reduced percentage of CYP with SEN Support subject to a fixed term exclusion | KCC Data | Termly | 31.5% (AY 2018-19) | 31.1% | Target | Target |  | Target |  | Target | Katherine Atkinson | 845 of 2,636 pupils excluded on one or more occasion. SEN provision of pupils sourced from Autumn 19 or Summer 19 or Spring 19 returns. The SEN provision of 15 pupils returned as 'unknown', thus these pupils and their exclusions have been excluded from the dataset and calculations. National comparator (2017-18) 30.11% |  | Sep 19 to Oct 19 - 418 of 1,343 pupils excluded. 32 pupils excluded from dataset and calculation due to SEN provision is 'unknown'.
[5 empty] | 28% | 25% |  | 23% |  | 20%
[5 empty] | Actual | Actual |  | Actual |  | Actual
32.1%
Reduced number of CYP with SEN Support subject to a permanent exclusion | KCC Data | Termly | 25 (AY 2018-19) | 2 | Target | Target |  | Target |  | Target | Katherine Atkinson | Data currently for 4 months of the academic year so as data builds figure likely to rise.
[5 empty] | 14 | 12 |  | 10 |  | 8
[5 empty] | Actual | Actual |  | Actual |  | Actual
9
Reduced percentage of CYP with an EHCP on a reduced timetable (based on those schools completing a RTT return) | Digital Front Door and School Census Form | Termly | Summer Term 2018-19 2.3% | Unclear source of original baseline data - has been recalculated based on DFD & MI returns | Target | Target |  | Target |  | Target | Katherine Atkinson | Latest data provided for children on a reduced timetable for the Autumn 2019 term Are schools getting better at reporting RTT due to the SEND Inclusion workstream, or are more being put on RTTs due to delays with issuing EHCPs?
[5 empty] | 2.1% | 1.9% |  | 1.7% |  | 1.5%
[5 empty] | Actual | Actual |  | Actual |  | Actual
3.8%
Reduced percentage of CYP with SEN Support on a reduced timetable (based on those schools completing a RTT return) | Digital Front Door and School Census Form | Termly | Summer Term 2018-19 2.3% | Unclear source of original baseline data - has been recalculated based on DFD & MI returns | Target | Target |  | Target |  | Target | Katherine Atkinson | Latest data provided for children on a reduced timetable for the Autumn 2019 term Are schools getting better at reporting RTT due to the SEND Inclusion workstream, or are more being put on RTTs due to delays with issuing EHCPs?
[5 empty] | 2.1% | 1.9% |  | 1.7% |  | 1.5%
[5 empty] | Actual | Actual |  | Actual |  | Actual
2.9%
Increased percentage of Year R-11-aged CYP with an EHCP placed in mainstream schools | KCC Data | Termly | 45% | SEN2 2020 Cohort | Target | Target |  | Target |  | Target | Katherine Atkinson
[5 empty] | 47% | 49% |  | 51% |  | 53%
[5 empty] | Actual | Actual |  | Actual |  | Actual
44.2%
Ensure the percentage of CYP with an EHCP who are NEET is below the national figure | Core+ CCIS | Termly (recognising there is seasonal fluctuation in NEET figures) | Average of Dec 18, Jan & Feb 19 data Kent EHCP 10.5% ALL 6.4% National EHCP 9.2% ALL 5.5% | Baseline figures were inaccurate and didn’t take into account national comparative data | Target | Target |  | Target |  | Target | Katherine Atkinson | Latest data provided for December 2019
[5 empty] | <9% | <9% |  | <9% |  | <9%
[5 empty] | Actual | Actual |  | Actual |  | Actual
6.1%
Increase the number of CYP with an EHCP aged 16-25 accessing Supported Employment | TEP Supported Employment | Annually (but need to monitor progress towards target) | 16-25 receiving supported employment 2018-19: 146 16-25 supported internships: 78 (not included in the above figures) | To end of Oct - Supported Employment- 142 To end of Oct - Supported Internships- 88 Target will be exceeded | Target | Target |  | Target |  | Target | Alicia Moyles
Supported Employment 175 Supported Internships 95
[5 empty] | Actual | Actual |  | Actual |  | Actual
Supported employment - 165 Supported internships - 92
Significant increase in the percentage of parents that agree or strongly agree with the parental survey statements that they are confident the educational provider can meet needs and has the knowledge/ skills to do so (Primary phase) | Parental surveys Supplemented by feedback from the parent/carer forums | Six-monthly | 36.3% | Next version of the parent survey being designed & tested prior to rollout | December 2019 |  | June 2020 |  | December 2020 |  | Louise Burgess / Sharon McLoughlin | Next parental survey planned for deployment in early June, once we have shared the 'you said, we did' from the first survey
[5 empty] | Target |  | Target |  | Target
[5 empty] | 46% |  | 51% |  | 56%
[5 empty] | Actual |  | Actual |  | Actual
Significant increase in the percentage of parents that agree or strongly agree with the parental survey statements that they are confident the educational provider can meet needs and has the knowledge/ skills to do so (Secondary) | Parental surveys Supplemented by feedback from the parent/carer forums | Six-monthly | 34.5% | Next version of the parent survey being designed & tested prior to rollout | Target |  | Target |  | Target |  | Louise Burgess / Sharon McLoughlin | Next parental survey planned for deployment in early June, once we have shared the 'you said, we did' from the first survey
[5 empty] | 45% |  | 50% |  | 55%
[5 empty] | Actual |  | Actual |  | Actual

## B4
B: Inclusive Practice and the Outcomes, Progress and Attainment of Children and Young People 4: The poor standards achieved, and progress made, by children and young people with SEND
Measures/indicators of success | Data source | Frequency | Baseline | Targets & Actuals |  | Responsibility for updating | Comments | RAG
Increased percentage of CYP with SEN Support achieving the expected standard in Reading, Writing & Maths at KS2 | DfE | Annual | 2018 Kent: 24 National: 24 | Target 2019 | Target 2020 | Katherine Atkinson | The 2019 National attainment % is 25%, 2% lower than Kent attainment. This is a 3% increase since 2018 for Kent compared to a 1% increase for National
|  |  |  | 25 | 26
|  |  |  | Actual | Actual
27
Improved progress score for CYP with SEN Support in Reading at KS2 | DfE | Annual | 2018 Kent: -1.2 National: -1.0 | Target 2019 | Target 2020 | Katherine Atkinson | The 2019 National progress score for Reading is -1.0, the same as 2018. Kent's progress score has declined since 2018
|  |  |  | -1.1 | -1
|  |  |  | Actual | Actual
-1.4
Improved progress score for CYP with SEN Support in Writing at KS2 | DfE | Annual | 2018 Kent: -1.7 National: -1.8 | Target 2019 | Target 2020 | Katherine Atkinson | The 2019 National progress score for Writing is -1.7, the same as Kent. This represents a minimal improvement for National, the Kent figure is the same as 2018.
|  |  |  | -1.6 | -1.5
|  |  |  | Actual | Actual
-1.7
Improved progress score for CYP with SEN Support in Maths at KS2 | DfE | Annual | 2018 Kent: -1.7 National: -1.0 | Target 2019 | Target 2020 | Katherine Atkinson | The 2019 National progress score for Maths is -1.0, the same as 2018. Kent's progress score has declined slightly since 2018.
|  |  |  | -1.6 | -1.5
|  |  |  | Actual | Actual
-1.9
Improved Attainment 8 score for CYP with SEN Support at KS4 | DfE | Annual | 2018 Kent: 33.7 National: 32.2 | Target 2019 | Target 2020 | Katherine Atkinson | Currently provisional data. DfE publication day has been pushed back to 6th February 2020
|  |  |  | 32 | 30
|  |  |  | Actual | Actual
34.4
Improved Progress 8 score for CYP with SEN Support at KS4 | DfE | Annual | 2018 Kent: -0.62 National: -0.43 | Target 2019 | Target 2020 | Katherine Atkinson | Currently provisional data. DfE publication day has been pushed back to 6th February 2020
|  |  |  | -0.5 | -0.4
|  |  |  | Actual | Actual
-0.71
N.B. The more positive the score the better for all above indicators

## B5
B: Inclusive Practice and the Outcomes, Progress and Attainment of Children and Young People 5: The lack of effective systems to track and improve outcomes for those children and young people whose progress to date has been limited by weaknesses in provision
Measures/indicators of success | Data source | Frequency | Baseline | INTERIM (Sept/Oct combined data) OR Commentary | Targets & Actuals | [5 empty] | Responsibility for updating | Comments | RAG
Percentage of CYP on track to achieve their end of key stage outcomes (for those annual reviews not taking place in the final year of the key stage) | EHCP Annual Reviews | Termly | New recording process to be fully implemented by September 2019 | New process in place. No data currently available | Autumn 2019 | Spring 2020 |  | Summer 2020 |  | Autumn 2020 | Louise Burgess | New process in place. No data currently available. New recording expectations not fully in place.
[5 empty] | Target | Target |  | Target |  | Target
[5 empty] | 50% | 52% |  | 55% |  | 57%
[5 empty] | Actual | Actual |  | Actual |  | Actual
Percentage of CYP who achieve at least 50% of their EHCP outcomes by the end of the key stage | EHCP Annual Reviews | Termly | New recording process to be fully implemented by September 2019 | New process in place. No data currently available | Target | Target |  | Target |  | Target | Louise Burgess | New process in place. No data currently available. New recording expectations not fully in place.
[5 empty] | 70% | 72% |  | 75% |  | 77%
[5 empty] | Actual | Actual |  | Actual |  | Actual
Ensure the percentage of CYP with an EHCP who are NEET is below the national figure | Core+ CCIS | Termly (recognising there is seasonal fluctuation in NEET figures) | Average of Dec 18, Jan & Feb 19 data Kent EHCP 10.5% ALL 6.4% National EHCP 9.2% ALL 5.5% | Baseline figures were inaccurate and didn’t take into account national comparative data | Target | Target |  | Target |  | Target | Katherine Atkinson | Based on December 2019 data
[5 empty] | <9% | <9% |  | <9% |  | <9%
[5 empty] | Actual | Actual |  | Actual |  | Actual
6.1%
Increased percentage of schools using robust and effective systems for the tracking of pupil attainment and behaviour | PEO audits of a sample of schools every term | Termly | Baseline in Autumn 2019 and set targets to improve from that position |  | December 2019 |  | June 2020 |  | December 2020 |  | Louise Burgess
[5 empty] | Target |  | Target |  | Target
[5 empty] | TBC |  | TBC |  | TBC
[5 empty] | Actual |  | Actual |  | Actual

## C6
C: Quality of Education, Health and Care Plans 6: The inconsistent quality of the EHC process; the lack of up to date assessments and limited contributions from health and care professionals; the poor processes to check and review the quality of EHC plans
Measures/indicators of success | Data source | Frequency | Baseline | INTERIM (Sept/Oct combined data) OR Commentary | Targets & Actuals | [5 empty] | Responsibility for updating | Comments | RAG
Significant increase in the percentage of parents satisfied with all steps of the statutory assessment process and the EHCP | Parental surveys | Six-monthly | 12.8% | Next version of the parent survey being designed & tested prior to rollout | December 2019 |  | June 2020 |  | December 2020 |  | Louise Burgess / Sharon McLoughlin | Next parental survey planned for deployment in early June, once we have shared the 'you said, we did' from the first survey
[5 empty] | Target |  | Target |  | Target
[5 empty] | 23% |  | 28% |  | 33%
[5 empty] | Actual |  | Actual |  | Actual
Increase in the percentage of new EHCPs that are completed within statutory timescales | Synergy | Termly | 29% | 28.9% (rolling 12 months) 23.5% (avg Sept & Oct) | Autumn 2019 | Spring 2020 |  | Summer 2020 |  | Autumn 2020 | Katherine Atkinson | National data 2018 = 60.1 % South East 2018: 51.0% Kent rolling 12 months to December 2019 = 34.5%
[5 empty] | Target | Target |  | Target |  | Target
[5 empty] | 40% | 45% |  | 50% |  | 60%
[5 empty] | Actual | Actual |  | Actual |  | Actual
December = 20.6% Rolling 12 months = 34.5%
Reduction in number of complaints regarding SEND | Complaints teams | Monthly | 2018-19 - 161 complaints (Monthly average = 13.4) | Q2 Total = 54 (July = 22, August = 15, Sept = 17) Monthly average = 18 | December 2019 | April 2020 |  | July 2020 |  | December 2020 | Claire Thomson | Q3 Total = 53 (Oct = 22, Nov = 21, Dec, 10); monthly average 17.7. 41.5% of complaints in Q3 were responded to in 20 working days, down from 64.8% in Q2. Future reporting will include the % of complaints that were upheld/partially upheld.
[5 empty] | Target | Target |  | Target |  | Target
[5 empty] | 12 | 12 |  | 12 |  | 12
[5 empty] | Actual | Actual |  | Actual |  | Actual
17.7
Reduction in the number of appeals received | Tribunals data | Monthly Average | 42 average per month | September - 40 October - 37 | Target | Target |  | Target |  | Target | Louise Burgess
[5 empty] | 39 | 36 |  | 33 |  | 30
[5 empty] | Actual | Actual |  | Actual |  | Actual
12

## D7
D: Joint commissioning and Governance 7: The inability of current joint commissioning arrangements to address known gaps and eliminate longstanding weaknesses in the services for children and young people with SEND
Measures/indicators of success | Data source | Frequency | Baseline | INTERIM (Q2 19-20) | Targets & Actuals |  |  |  |  | Responsibility for updating | Comments | RAG
Established Joint Commissioning Team | NHS/KCC | Monthly | N/A | On Track | Q3 19-20 | Q4 19-20 | Q1 20-21 | Q2 20-21 | Q3 20-21 | Rachel Jones | Initial priorities agreed through JCCG. Draft framework developed. External consultancy (NHSE & Council for disabled children) supporting development of an outcomes based commissioning framework
[5 empty] | Target | Target | Target | Target | Target
[5 empty] | N/A | Team established
[5 empty] | Actual | Actual | Actual | Actual | Actual
On Track
Percentage of schools that have access to a health supported special school nursing service | NHS | Quarterly | 45% | 77% | Target | Target | Target | Target | Target | Rachel Jones | Model approved by JCCG for cover across the county. Financial agreement being pursued
[5 empty] | Network established | 70% | 80% | 90% | 100%
[5 empty] | Actual | Actual | Actual | Actual | Actual
77%
Equitable speech and language therapy | NHS | Quarterly | Baseline data to be agreed when review complete |  | Target | Target | Target | Target | Target | Rachel Jones | Previous work with external consultant being revisited. New SRO appointed to lead workstream. Multiagency agency working group established. T&F group currently reviewing and developing standardised data set
[5 empty] | TBC | TBC | TBC | TBC | TBC
[5 empty] | Actual | Actual | Actual | Actual | Actual
Not yet available
Percentage of children and young people who have NHS supported vision screening and follow up | NHS | Quarterly | 55% | 75% | Target | Target | Target | Target | Target | Rachel Jones | County wide coverage in place. NHSE are providing additional new cover from Apr 2020 for special schools
[5 empty] | 65% | 75% | 85% | 95% | 100%
[5 empty] | Actual | Actual | Actual | Actual | Actual
75%
D: Joint commissioning and Governance 8: The governance of SEND arrangements across the EHC system at strategic and operational level and absence of robust action plans to address known weaknesses
NO DATA INDICATORS

## E9
E: Service Provision 9: The unacceptable waiting times for children and young people to be seen by some health services, particularly CAMHS, tier two services, SALT, the wheelchair service, and ASD and ADHD assessment and reviews
Measures/indicators of success | Data source | Frequency | Baseline | INTERIM (Q2 19-20) | Targets & Actuals |  |  |  |  | Responsibility for updating | Comments | RAG
Percentage of young people meeting 18 week referral times for ASD/ADHD assessments | NHS | Quarterly | 15% | 15% | Q3 19-20 | Q4 19-20 | Q1 20-21 | Q2 20-21 | Q3 20-21 | Rachel Jones | Current wait is 2 years, which has reduced from 4 years in 2018. Referrals for the ND service continue to grow significantly and exceed expected levels. Work is being done to review and refine the current NDLDS pathway and to develop a new, multi agency pathway - deadline is April 20. Patients are involved in pathway redesign and a clinical reference group has been formed to support this work.
[5 empty] | Target | Target | Target | Target | Target
[5 empty] | 20% | 25% | 30% | 35% | 45%
[5 empty] | Actual | Actual | Actual | Actual | Actual
15%
Percentage of young people meeting 18 week referral to treatment target for (CYMHPS) | NHS | Quarterly | 50% | 77% | Target | Target | Target | Target | Target | Rachel Jones | Each locality has a trajectory to reach target and 5 CCG's areas have already achieved this. Compared to National figures, Kent is a high achiever
[5 empty] | 55% | 70% | 75% | 80% | At least 92%
[5 empty] | Actual | Actual | Actual | Actual | Actual
77%
% of those identified by health visitors and/ or early years providers as part of the new model including the pilot phase at 2 years as requiring an integrated review, who are offered one | NHS | Quarterly | N/A | 0% | Target | Target | Target | Target | Target | Vicky Tovey | A review of the integration of the Two Year Progress Check and the 2 - 2.5 Year Old Health Check is complete and has been overseen by a director level monitoring group. User feedback from the original pilot has been used to support the design of a new integrated model which is being tested in theory with the workforce and service users in March. The new model will be implemented in a phased way starting in May 2020.
[5 empty] | 0% | 0% | 80% | 90% | 100%
[5 empty] | Actual | Actual | Actual | Actual | Actual
0%
% of those identified by health visitors and/or early years providers as part the new model including the pilot phase at 2 years as requiring an integrated check, who attend one | NHS | Quarterly | N/A | 0% | Target | Target | Target | Target | Target | Vicky Tovey
[5 empty] | 0% | 0% | 70% | 75% | 80%
[5 empty] | Actual | Actual | Actual | Actual | Actual
0%
Percentage of YP over 14 with a learning disability have an annual health check | NHS | Quarterly | 41% | 41% | Target | Target | Target | Target | Target | Rachel Jones | A plan has been developed led by PH. This includes having clinical leads and working with providers
[5 empty] | 50% | 55% | 60% | 68% | 75%
[5 empty] | Actual | Actual | Actual | Actual | Actual
41%
Percentage of YP meeting 18 week referral to treatment target for wheelchair assessments and provision | NHS | Quarterly | 76% | 76% | Target | Target | Target | Target | Target | Rachel Jones | This is being monitored monthly/weekly via contract meetings
[5 empty] | 80% | 87% | 92% | 92% | 92%
[5 empty] | Actual | Actual | Actual | Actual | Actual
89%